## BLANK Product Backlog
PRODUCT BACKLOG REPORT
USER STORIES
ID | AS A … | I WANT … | SO THAT I CAN … | FEATURE NAME | ESTIMATED(SIZE) | ESTIMATED EFFORT(IN HRS) | SPRINT NO.
1 | Employee | login page | login myself and get access to dashboard containing order list button. | Login | Medium | 10 | 4
2 | Employee | forgot password button in the login page | retrieve my password through an email | Forgot Password | Medium | 5 | 5
3 | Employee | order list page | view orders of customers for verification | View Orders | Large | 14 | 4
4 | Employee | logout button | logout when my work is done | Logout | Small | 7 | 5
5 | Manager | login page | login myself and get access to the dashboard containing product list, order list and create products. | Login | Medium | 10 | 4
6 | Manager | forgot password button in the login page | retrieve my password through an email | Forgot Password | Small | 5 | 5
7 | Manager | a product list page | edit existing products | Edit Products | Large | 20 | 3
8 | Manager | order list page | view all orders of customers | View Orders | Medium | 14 | 3
9 | Manager | create products page | add new products | Add Product | Large | 16 | 3
10 | Manager | logout button | logout when my work is done | Logout | Small | 7 | 5
11 | Customer | products page | view the available products | View Products | Medium | 16 | 1
12 | Customer | ‘buy now’ button for every product in the products page | add products to my cart | Add to Cart | Medium | 12 | 1
13 | Customer | update quantity button | update the quantity of products in my cart | Update Quantity | Large | 20 | 1
14 | Customer | edit customer info button in confirm shopping cart page | edit my information | Edit Customer Info | Small | 7 | 3
15 | Customer | edit cart button in confirm shopping cart page | edit my cart | Edit Cart | Medium | 14 | 2
16 | Customer | pay button | make the paytment | Payment | Medium | 12 | 1
17 | Customer | bill button in the cart finalize page | view order summary/bill | Bill | Small | 7 | 2
18 | Customer | download bill button in bill summary page | download the bill | Download Bill | Small | 5 | 2
TOTAL | [5 empty] | 201